## Slide 1
Wind Farm Project Development, WiSe 2024/25
Team 3: Wind Farm Project in Gujarat, India
Presented by: Matriculation No.
Mozafary Mostafa 750247
Patil Rahul 750532
Soni Karan 760153
Guided by: Prof. Marina Blohm
Date : 15.01.2025
Place: Flensburg

## Slide 2: Overview
Overview of wind farm development in Gujarat
Requirement and Criterial
Wind Area selection
Grid infrastructure and cable routing
Project development timeline
Strategies community engagement
Land Leasing
Addressing conflicting Interests
9. Logistics and Transformation
10. Profitability Analysis
11. Results
12. Long Term Strategy
13. Barriers and Obstacles
14. Conclusion
15. References

## Slide 3: 1. Overview of Wind Farm Development in Gujarat
India:
India ranks fourth in terms of installed wind power capacity.
Several Large Wind Farm: Tamil Nadu, Gujarat, Maharashtra.
Gujarat:
As May 2024, makes it the leading state in India for wind energy.
11,823 MW installed wind power capacity
Second rank, Tamil Nadu 10,743 MW
Why?
Geographic advantages, Government supports, Land policy, Tax benefits.

## Slide 4: 2. Requirement and Criterial
Guidelines for micro siting of wind turbine:
Maintain a distance of (D-Rotor Diameter) distance perpendicular to the predominant wind direction and distance in the predominant wind direction
Maintain a distance of (Hub Height+ Half Rotor Diameter +5 meters) from Public Roads, railway tracks, highways, buildings, public institutions and EHV lines
Application for Hazardous Waste (Grease, Coolant oil and Lubricating oil) Authorisation
Permission for forest department
Eco-Sensitive zones (wildlife sanctuaries)
NOC from Airport authority of India and Ministry of defence

## Slide 5: 3. Wind Area Selection
Analyse Wind Farm:
Wind speed data at 100m height
Coordinate Reference System: WGS 84/ UTM zone 43N, Authority ID: EPSG:32643
Integrated wind speed data onto the white map layer [Use the clip Raster by Mask Layer Tool]
GIS Layers | Distances [m]
Buildings | 250
Forests | 10,000
Military Areas | 10,000
Railways/ Industrial | 250
Roads | 250
Airports/ Airfields | 20,000
Rivers | 250

## Slide 6: 3. Wind Area Selection

## Slide 7: 3. Wind Area Selection

## Slide 8: 4. Grid Infrastructure and Cable Routing

## Slide 9: 5. Project Development Timeline

## Slide 10: 6. Strategies of Community engagement
Community Meeting
Engage Local Leaders
Transparency
Benefit Sharing
Regular Updates
Community Feedback
Raise Awareness
Long Term Engagement

## Slide 11: 7. Land Leasing

## Slide 12: 8. Addressing Conflicting Interests

## Slide 13: 9. Logistics and Transformation
NH48
NH4
NE1
NH64
NH27
754k
1
2
3
4
Wind Turbine Manufacturing components | Manufacturing Locations | Distance between Manufacturing location to Wind farm [km]
Nacelle | Daman, Gujarat, India | 743
Nacelle Cover | Daman, Gujarat, India | 743
Hub | Daman, Gujarat, India | 743
Rotor Blades | Bhuj, Gujarat, India | 57
Tower | Gandhidham, Gujarat, India | 136
Electrical | Vadodara, India | 544
Location: Poladia, Gujarat, India
Why Suzlon company wind turbine?
Manufacturing in Gujarat
Government provides incentives (Made in India)

## Slide 14: 10. Profitability Analysis
Chart: 
| 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044
Income | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166 | 1564892.6166
Chart: Operating costs
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045
Betriebskosten | 540096.1945 | 551799.0804 | 563853.0528 | 426268.6444 | 439056.7037 | 452228.4048 | 465795.2569 | 479769.1146 | 494162.1881 | 508987.0537 | 524256.6653 | 539984.3653 | 556183.8963 | 572869.4131 | 590055.4955 | 607757.1604 | 625989.8752 | 644769.5715 | 664112.6586 | 684036.0384

## Slide 15: 10. Profitability Analysis
Chart: 
| Eigenkapital | Fremdkapital
 | 0.2727 | 0.7273
Chart: Debt service installment loan
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045
Repayment | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366 | 456014.366
Interest | 232567.3267 | 232567.3267 | 232567.3267 | 225727.1112 | 212046.6802 | 198366.2492 | 184685.8182 | 171005.3873 | 157324.9563 | 143644.5253 | 129964.0943 | 116283.6633 | 102603.2324 | 88922.8014 | 75242.3704 | 61561.9394 | 47881.5084 | 34201.0775 | 20520.6465 | 6840.2155

## Slide 16: 10. Profitability Analysis
Chart: 
Chart: Taxes
| 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045
Steuer | 994.8621 | 0 | 0 | 15149.9994 | 15253.3494 | 15312.2679 | 15325.4221 | 15291.4389 | 15208.9042 | 15076.3615 | 14892.3105 | 14655.2061 | 14363.4565 | 14015.4225 | 102029.0985 | 101563.3793 | 101036.1566 | 100445.5852 | 99789.7647 | 99066.7375

## Slide 17: 11. Results
 | Value | Unit
NPV | 42,64,328 | EUR
NPV costs | -58,77,099 | EUR
NPV kWh | 57,22,36,284 | EUR
IRR | 19.362 % | 
LEC | 0.0289 | EUR
Min. DSCR | 1.64 | 
ADSCR | 1.70 | 
NPV = Net Present Value, IRR = Internal Rate of Return, LEC = Levelized Cost of Energy, Min. DSCR = Minimum Debt Service Coverage Ratio, ADSCR = Average Debt Service Coverage Ratio
Positive NPV
Impressive IRR
Project promises cost efficiency and financial stability
Highly profitable project

## Slide 18: 12. Long Term Strategy
Vision and Goals:
By 2030:
Achieve an installed wind energy capacity of 15 GW.
Increase the share of wind energy to 20% of the state's total energy mix.
Launch the first phase of offshore wind projects.
By 2050:
Establish Gujarat as a global leader in wind energy.
Fully integrate smart grid solutions for efficient energy distribution.
Achieve a 50% reduction in carbon emissions from energy production.
Strategy to achieve goal:
Improve Policy support
Advanced turbine technologies
Upgrade infrastructure
Integrating smart grid
Encouraging community engagement
Spend more money in research and development of wind turbine
Energy storage system

## Slide 19: 13. Barriers and Obstacles
High Initial Costs
Land Use Conflicts
Environmental Concerns
Maintenance Issues
Grid Integration
Standardization and Quality Control
Limited Awareness
Preference for Solar Energy

## Slide 20: 14. Conclusion
Location of Wind farm Perspective:
Taking advantage of Gujarat favourable policy environment
Manufacturing location of Suzlon company
Profit Perspective:
Project Achieves a positive NPV
Impressive IRR
Economic Perspective:
Reducing carbon emissions
Job creation
Local manufacturing

## Slide 21: 15. References